## MVP Costing
S. No. | Role | Count | Monthly Rate | Months | Totals | Comments
1 | Product Owner | 2 | 70000 | 4 | 560000 | Alok to provide initial support & share role as demand increases
2 | Scrum Master | 1 | 60000 | 4 | 240000 | Dedicated to scrum practice
3 | Developer | 4 | 60000 | 4 | 960000 | Tech experts
4 | UX Developer | 1 | 60000 | 4 | 240000 | Tech experts
5 | System Architect | 1 | 100000 | 4 | 400000 | Experienced
6 | Business Analyst | 1 | 50000 | 4 | 200000 | Need someone with good experience
7 | Project Manager | 1 | 100000 | 4 | 400000 | Multi dimensional role, Abhijeet can potentially support it.
Notes / Open Queries
Location of resources and POC |  |  |  | Most developers could be in Pune with Architect, some UK contacts could pitch in too
Approach of team connect & schedule |  |  |  | Scrum rituals will be established
Lead time of procurement & training |  |  |  | Need to review market status & decide, could take 2 weeks (end of March week 1). Still use the time to complete SOW & any other documentation work ( Shrikant Ji).
Role definition (?) |  |  |  | Can put in SOW
SK - High level system design & architecture |  |  |  | To be prioritized 1st sprint
SK - All platforms and system licenses |  |  |  | Open source framework for development and licenses softwares to follow. Most paid services are pay per use, so not immediate impacts. Alok has high level costing for some external support needs.
SK - Infrastructure hardware/server requirements |  |  |  | Not necessary with cloud support
SK - Add value of tech components to financial model |  |  |  | Action for Alok/Rajesh
Immediate support actions |  |  |  | SOW, Resourcing
Next meeting & prospective agenda |  |  |  | Follow-up conversation Saturday 27th Feb 6PM IST
AOB |  |  |  | Share this note with all Shri Ji's team cost is currently not incorporated yet in the proposal Share status on other parallel conversation on the solution